## Inbound Requirements
Requirements # | Category | Type | Requirement | Details | Priority | Status
REQ-001 | System Configuration | Technical | Time Zone Configuration | Configure all system operations, schedules, hours of operation, and time-based routing decisions to use Eastern Time (ET) as the primary timezone reference | Required | Not Started
REQ-002 | Inbound Lines & Hours | Configuration | Finance Line Hours of Operation | Monday - Friday, 8:00 AM - 5:00 PM Eastern Time. All times outside this window (before 8 AM, after 5 PM, weekends) are considered after-hours | Required | Not Started
REQ-003 | Inbound Lines & Hours | Configuration | Customer Service Line Hours of Operation | Monday - Friday, 8:00 AM - 7:00 PM Eastern Time (extends 2 hours beyond Finance). All times outside this window are considered after-hours | Required | Not Started
REQ-004 | Inbound Lines & Hours | Configuration | Customer Service Line Catch-All Function | Customer Service line serves as catch-all for all unused 800 numbers and legacy queue numbers. All legacy/discontinued customer-facing numbers must route to Customer Service line | Required | Not Started
REQ-005 | IVR & Call Flow | Call Routing | Finance Line Call Flow Sequence | Sequential call flow: Step 1: Emergency Broadcast check → Step 2: Holiday check → Step 3: Temporary closure check → Step 4: Hours of operation check → Step 5: Finance queue routing. Each step follows specific logic defined in subsequent requirements | Required | Not Started
REQ-006 | IVR & Call Flow | Call Routing | Finance Line Emergency Broadcast Behavior | If emergency broadcast ACTIVE: Play emergency message, then continue to holiday check. If INACTIVE: Skip to holiday check. Emergency broadcast does NOT terminate calls, only adds informational message | Required | Not Started
REQ-007 | IVR & Call Flow | Call Routing | Finance Line Holiday Routing | If current date matches configured holiday: Play holiday greeting → Route to Finance voicemail → END. If NOT holiday: Continue to temporary closure check | Required | Not Started
REQ-008 | IVR & Call Flow | Call Routing | Finance Line Temporary Closure Routing | If temporary closure active for current date/time: Play temporary closure message → Route to Finance voicemail → END. If no temporary closure: Continue to hours check | Required | Not Started
REQ-009 | IVR & Call Flow | Call Routing | Finance Line Hours Check Routing | If WITHIN business hours (8 AM - 5 PM ET Mon-Fri): Route to Finance queue. If OUTSIDE business hours: Play after-hours message → Route to Finance voicemail → END | Required | Not Started
REQ-010 | IVR & Call Flow | Call Routing | Customer Service Line Call Flow Sequence | Sequential call flow: Step 1: Emergency Broadcast check → Step 2: Holiday check → Step 3: Temporary closure check → Step 4: Hours check → Step 5: IVR menu presentation (3 options) → Step 6: Route based on selection | Required | Not Started
REQ-011 | IVR & Call Flow | Call Routing | Customer Service Line Emergency Broadcast Behavior | If emergency broadcast ACTIVE: Play emergency message, then continue to holiday check. If INACTIVE: Skip to holiday check. Emergency broadcast does NOT terminate calls | Required | Not Started
REQ-012 | IVR & Call Flow | Call Routing | Customer Service Line Holiday Routing | If current date matches configured holiday: Play holiday greeting → Route to Customer Service voicemail → END. If NOT holiday: Continue to temporary closure check | Required | Not Started
REQ-013 | IVR & Call Flow | Call Routing | Customer Service Line Temporary Closure Routing | If temporary closure active for current date/time: Play temporary closure message → Route to Customer Service voicemail → END. If no temporary closure: Continue to hours check | Required | Not Started
REQ-014 | IVR & Call Flow | Call Routing | Customer Service Line Hours Check | If WITHIN business hours (8 AM - 7 PM ET Mon-Fri): Continue to IVR menu. If OUTSIDE business hours: Play after-hours message → Route to Customer Service voicemail → END | Required | Not Started
REQ-015 | IVR & Call Flow | IVR Menu | Customer Service IVR Menu Options | Present 3-option menu: Press 1 = Transfer to Finance Queue ¦ Press 2 = Customer Service - Place Order Queue ¦ Press 3 = Customer Service - Questions Queue. Menu must include clear prompts for each option | Required | Not Started
REQ-016 | IVR & Call Flow | IVR Menu | IVR Menu Error Handling - Retry Logic | Maximum 3 retry attempts with 10-second intervals. After invalid entry or timeout: Attempt 1 - Play invalid selection message ¦ Attempt 2 - Replay menu with invalid message ¦ Attempt 3 - Replay menu with invalid message ¦ After 3rd failure: Route to Customer Service Questions queue (default). Industry standard error handling | Required | Not Started
REQ-017 | IVR & Call Flow | IVR Menu | IVR Menu Routing - Press 1 Finance | When caller presses 1: Transfer call to Finance Queue. Apply Finance queue configuration (hold music, announcements, agent routing) | Required | Not Started
REQ-018 | IVR & Call Flow | IVR Menu | IVR Menu Routing - Press 2 Place Order | When caller presses 2: Route to Customer Service - Place Order Queue. Apply Place Order queue configuration with all CS agents assigned | Required | Not Started
REQ-019 | IVR & Call Flow | IVR Menu | IVR Menu Routing - Press 3 Questions | When caller presses 3: Route to Customer Service - Questions Queue. Apply Questions queue configuration with experienced agents only | Required | Not Started
REQ-020 | Emergency Broadcast | Feature | Emergency Broadcast Internal Access Number | Create internal access phone number (not published to customers) for administrators to activate/deactivate emergency broadcasts. Only authorized administrators can access | Required | Not Started
REQ-021 | Emergency Broadcast | Feature | Emergency Broadcast Activation Interface | IVR menu on internal access number with options to: Activate emergency broadcast ¦ Deactivate emergency broadcast ¦ Record/update emergency message (optional if using text-to-speech) | Required | Not Started
REQ-022 | Emergency Broadcast | Feature | Emergency Broadcast Active Behavior | When ACTIVE: Play pre-recorded emergency message immediately when call enters system (Finance or Customer Service line) → Then continue through normal call flow (holiday → temporary closure → hours → queue routing). Broadcast does NOT terminate calls or route to voicemail | Required | Not Started
REQ-023 | Emergency Broadcast | Feature | Emergency Broadcast Inactive Behavior | When INACTIVE: Skip emergency broadcast step entirely. Call proceeds directly to Holiday check with no indication to caller that feature exists | Required | Not Started
REQ-024 | Emergency Broadcast | Feature | Emergency Broadcast Message Management | Primary method: Five9 text-to-speech for rapid updates. Administrators can update message text in Five9 without re-recording. Alternative: Upload pre-recorded professional audio if customer prefers. Messages apply to ALL lines when active | Required | Not Started
REQ-025 | Emergency Broadcast | Documentation | Emergency Broadcast Administrator Training | Provide training and documentation to designated administrators (Michelle, Nicole, others TBD) on activation/deactivation procedures. Document use cases: weather disruptions, emergency closures, system outages | Required | Not Started
REQ-026 | Holiday Configuration | Schedule | Holiday Schedule Configuration | Configure custom holiday schedule based on customer-provided list. Customer does NOT observe all federal holidays. Confirmed holidays include: New Year's Day, MLK Day, Good Friday, Memorial Day. Complete list to be provided by Michelle | Required | Not Started
REQ-027 | Holiday Configuration | Schedule | Holiday Date Format Support | Support both recurring annual holidays (e.g., 'First Monday in September' for Labor Day) and fixed-date holidays (e.g., 'July 4' for Independence Day). Convert customer-provided dates to proper system format | Required | Not Started
REQ-028 | Holiday Configuration | Call Flow | Holiday Call Flow - Finance Line | When holiday detected on Finance line: Play holiday greeting message → Route immediately to Finance Voicemail queue → END. Do NOT present IVR menu or queue options. Do NOT route to agents | Required | Not Started
REQ-029 | Holiday Configuration | Call Flow | Holiday Call Flow - Customer Service Line | When holiday detected on Customer Service line: Play holiday greeting message → Route immediately to Customer Service Voicemail queue → END. Do NOT present IVR menu or queue options. Do NOT route to agents | Required | Not Started
REQ-030 | Holiday Configuration | Voicemail | Holiday Voicemail Processing | Voicemails left on holidays become available to agents on next business day. Agents retrieve via 'Ready - All' status selection. High-priority voicemails processed first on return day | Required | Not Started
REQ-031 | Temporary Closure | Feature | Temporary Closure Scheduling | Support date AND time-specific closures (e.g., 'February 15, 2026, 11:30 AM - 12:00 PM'). Support line-specific closures: All lines simultaneously OR Finance only OR Customer Service only. Support recurring closures (e.g., 'Every other Wednesday at 11:30 AM') | Required | Not Started
REQ-032 | Temporary Closure | Feature | Temporary Closure Use Cases | Company meetings (twice monthly, Wednesdays 11:30 AM - 12:00 PM ET, all lines closed) ¦ Departmental events (e.g., Customer Service Week, CS queue only closed 1-2 hours) ¦ Ad-hoc closures (emergency meetings, facility issues, variable duration 30 min - 3 hours) | Required | Not Started
REQ-033 | Temporary Closure | Feature | Temporary Closure Message Customization | Use Five9 text-to-speech for rapid updates. Administrator can modify message text without technical support. Support immediate updates (e.g., meeting runs late, extend closure time). Messages include: reason for closure, expected reopening time, alternative contact methods | Required | Not Started
REQ-034 | Temporary Closure | Call Flow | Temporary Closure Active Call Flow | When active temporary closure detected: Play temporary closure message → Route immediately to appropriate voicemail queue → END. Do NOT present IVR menu. Do NOT route to agents | Required | Not Started
REQ-035 | Temporary Closure | Feature | Temporary Closure Activation Controls | Scheduled activation: System automatically activates at configured start time ¦ Scheduled deactivation: System automatically deactivates at end time ¦ Manual override: Admin can deactivate early if event ends sooner ¦ Manual activation: Admin can activate immediately for unplanned closures | Required | Not Started
REQ-036 | Temporary Closure | Documentation | Temporary Closure Administrator Interface | Provide simple web-based interface in Five9 Admin Application for designated administrators (Michelle, Nicole). Training provided during UAT on creating, modifying, and deleting temporary closure schedules | Required | Not Started
REQ-037 | After-Hours Schedule | Call Flow | Finance Line After-Hours Definition | After-hours = Monday-Friday before 8:00 AM or after 5:00 PM ET, All day Saturday, All day Sunday | Required | Not Started
REQ-038 | After-Hours Schedule | Call Flow | Customer Service Line After-Hours Definition | After-hours = Monday-Friday before 8:00 AM or after 7:00 PM ET, All day Saturday, All day Sunday | Required | Not Started
REQ-039 | After-Hours Schedule | Call Flow | After-Hours Routing Behavior | When after-hours detected: Play after-hours/night message → Route immediately to appropriate voicemail (Finance calls → Finance Voicemail ¦ CS calls → CS Voicemail). Do NOT present IVR menu. Do NOT queue calls. Do NOT route to agents | Required | Not Started
REQ-040 | After-Hours Schedule | Prompts | After-Hours Message Requirements | Line-specific messages stating: offices closed, business hours (5 PM for Finance / 7 PM for Customer Service), voicemail instructions, alternative contact methods (website URL, email address). Sample: 'Our offices are currently closed. Business hours are Monday-Friday, 8 AM to [5/7 PM] ET. Please leave detailed message with name, phone, reason for calling' | Required | Not Started
REQ-041 | After-Hours Schedule | Voicemail | After-Hours Voicemail Processing | Voicemails left after hours become available to agents on next business day. Agents retrieve via 'Ready - All' status. Processing priority per customer's internal policies | Required | Not Started
REQ-042 | Queue Configuration | Settings | Maximum Queue Time Setting | Recommended: 5 minutes (shorter than 10-minute default for better customer experience). After timeout: Route to appropriate voicemail queue. Customer expressed openness to Five9 best practice recommendations | Required | Not Started
REQ-043 | Queue Configuration | Settings | Queue When No Agents Logged In | Setting: YES - Allow queueing even when zero agents logged in. Behavior: If no agents in Available or Not Ready status, route immediately to voicemail. Prevents customers holding indefinitely with no possibility of agent connection | Required | Not Started
REQ-044 | Queue Configuration | Settings | Queue When All Agents Not Ready | Setting: YES - Allow queueing when agents logged in but all in Not Ready status. Behavior: Hold customer in queue as agents may become ready momentarily. Alternative option: Route to voicemail immediately (requires customer decision during configuration) | Required | Not Started
REQ-045 | Hold Experience | Configuration | Hold Music and Announcement Intervals | First announcement at 18 seconds after entering queue (position in queue/general message). Subsequent announcements every 30 seconds. Between announcements: Play music on hold continuously. Music must loop seamlessly without dead air | Required | Not Started
REQ-046 | Hold Experience | Configuration | Hold Announcement Content Options | First announcement: Position in queue, disclaimer, or general greeting ¦ Subsequent announcements: High call volume apology, Estimated wait time (if available), Alternative contact methods (website, email), Press 1 for voicemail option | Required | Not Started
REQ-047 | Hold Experience | Feature | Voicemail Option During Hold | Frequency: Offer voicemail option every 30 seconds during hold announcements. Action: Press 1 to leave voicemail → Immediately route to appropriate voicemail queue (Finance or Customer Service based on originating line). If no response: Continue hold cycle, offer again in next 30-second interval. Persist until agent answers, timeout, or disconnect | Required | Not Started
REQ-048 | Hold Experience | Configuration | Music on Hold File | Customer will provide custom music on hold file (or use Five9 default). File must be in proper format for Five9 system. Apply to all queues: Finance, CS Place Order, CS Questions | Required | Not Started
REQ-049 | Skills-Based Routing | Queue Design | Finance Queue Configuration | Single Finance queue for all Finance line calls. All Finance agents assigned to this queue. Apply general queue parameters (5 min max queue time, announcements, hold music, voicemail option). Timeout destination: Finance Voicemail. Press 1 during hold: Finance Voicemail | Required | Not Started
REQ-050 | Skills-Based Routing | Queue Design | Customer Service Place Order Queue Configuration | Call characteristics: Customers who know exactly what to order, straightforward transactions, lower complexity. Agent assignment: ALL Customer Service agents (including new hires and experienced). Apply queue parameters with 5 min timeout. Agent desktop displays 'CS Place Order' | Required | Not Started
REQ-051 | Skills-Based Routing | Queue Design | Customer Service Questions Queue Configuration | Call characteristics: Order status inquiries, complex product questions, troubleshooting, higher complexity requiring expertise. Agent assignment: SUBSET of CS agents - only experienced/tenured staff with proven expertise. Apply queue parameters with 5 min timeout. Agent desktop displays 'CS Questions' | Required | Not Started
REQ-052 | Skills-Based Routing | Configuration | Deprecate Regional Routing Logic | DO NOT IMPLEMENT area code-based routing. Previous system used regional queues (North, South, Central, West) based on area code mapping. This functionality has been removed and simplified. All CS agents now handle calls from all geographic regions | Required | Not Started
REQ-053 | Skills-Based Routing | Assignment | Agent Queue Assignment | Customer to provide list of which CS agents are assigned to Place Order queue (all agents) vs Questions queue (experienced agents only). Finance agents assigned to Finance queue. Agents may be assigned to multiple queues as appropriate | Required | Not Started
REQ-054 | Voicemail Configuration | Queue Setup | Voicemail Queue Structure | Create two voicemail queues: Finance Voicemail Queue (receives Finance line voicemails, accessed by Finance agents only) ¦ Customer Service Voicemail Queue (receives CS line voicemails, accessed by CS agents only) | Required | Not Started
REQ-055 | Voicemail Configuration | Prompts | Finance Voicemail Greeting | Professional greeting prompting caller to leave message. Sample: 'You have reached the Finance department at [Company]. Please leave your name, phone number, account number if available, and a detailed message. We will return your call within one business day.' Customer provides script; temporary text-to-speech used initially | Required | Not Started
REQ-056 | Voicemail Configuration | Prompts | Customer Service Voicemail Greeting | Professional greeting prompting caller to leave message. Sample: 'You have reached Customer Service at [Company]. Please leave your name, phone number, order number if available, and a detailed message. We will return your call within one business day.' Customer provides script; temporary text-to-speech used initially | Required | Not Started
REQ-057 | Voicemail Configuration | Agent Access | Voicemail Access Method | Agents select 'Ready - All' status in Five9 agent desktop to receive voicemail messages. Voicemails delivered one at a time similar to live calls. Agent clicks to play voicemail recording through headset/speakers | Required | Not Started
REQ-058 | Voicemail Configuration | Processing | Voicemail Playback and Processing | Agent listens to voicemail → Processes request (lookup customer, return call, process order without callback, escalate to appropriate department) → Agent dispositioning required (same as live calls) → Voicemail interaction logged in Five9 reporting | Required | Not Started
REQ-059 | Voicemail Configuration | Tracking | Voicemail Callback Tracking | Customer needs visibility into which voicemails have been returned vs pending. Implementation options: Disposition codes ('Voicemail - Returned Call' vs 'Voicemail - Left Message') ¦ Custom fields in NetSuite activity record ¦ Five9 reporting filters. Decision to be finalized during training/configuration phase | Required | Not Started
REQ-060 | Voicemail Configuration | Settings | Voicemail Recording Length and Capacity | Maximum recording length: 2-3 minutes (configurable, industry standard). Behavior after max length: Automatically end recording, save message, thank caller. Queue capacity: No practical limit, all voicemails accepted and queued. No overflow handling needed - voicemail always available as final destination | Required | Not Started
REQ-061 | Agent Desktop | Display | Finance Line Call Source Identification | Display label: 'Finance' (or equivalent clear identifier). Location: Visible in Five9 agent desktop call information panel. Timing: Must appear when call is alerting (before answer) or immediately upon connection. Purpose: Agent knows this is Finance line, prepares appropriate greeting | Required | Not Started
REQ-062 | Agent Desktop | Display | Customer Service Place Order Call Identification | Display label: 'CS Place Order' (or equivalent clear identifier). Location: Visible in agent desktop call information panel. Timing: Display when call alerting or immediately upon connection. Purpose: Agent knows customer wants to place order, prepares appropriate greeting | Required | Not Started
REQ-063 | Agent Desktop | Display | Customer Service Questions Call Identification | Display label: 'CS Questions' (or equivalent clear identifier). Location: Visible in agent desktop call information panel. Timing: Display when call alerting or immediately upon connection. Purpose: Agent knows customer has inquiry/issue, prepares for more complex interaction | Required | Not Started
REQ-064 | Agent Desktop | Display | Transferred Call Identification | For calls transferred from Customer Service IVR to Finance (Press 1): Display 'Finance' as primary label. Additional info (if possible): Indication that call originated from CS IVR transfer. Purpose: Finance agent understands customer already navigated menu | Required | Not Started
REQ-065 | Agent Desktop | Display | ANI Display Format | Display caller's phone number (Automatic Number Identification) prominently in agent desktop. Format: Standard US phone format (###) ###-####. Timing: Display immediately when call alerts | Required | Not Started
REQ-066 | Agent Desktop | Display | Standard Call Information Panel | Display: Caller phone number (ANI), Queue/Skill name (Finance, CS Place Order, CS Questions), Wait time (how long caller has been holding), Call type (inbound, outbound, internal), Date/time of call, Campaign/DNIS information (which phone number caller dialed) | Required | Not Started
REQ-067 | Agent Desktop | Display | NetSuite-Enhanced Information Display | Additional information if available: Caller name (if matched from NetSuite), Account/customer number (if matched), Previous interaction history (if available), VIP status or priority indicators (if customer uses this) | Optional | Not Started
REQ-068 | NetSuite Integration | Installation | NetSuite Package Installation - Sandbox | Install Five9 NetSuite SuiteApp package in customer's NetSuite Sandbox environment first. Package includes pre-built scripts, workflows, custom fields, and adapter interface. Sandbox must be refreshed copy of Production (not outdated). Five9 team has sandbox access credentials (confirmed) | Required | Not Started
REQ-069 | NetSuite Integration | Installation | NetSuite Package Installation - Production | After sandbox testing complete and customer approval: Install package in Production NetSuite environment. Customer provides Production credentials separately (security). Production testing before go-live. Rollback plan documented | Required | Not Started
REQ-070 | NetSuite Integration | Configuration | NetSuite Custom Fields Creation | Package creates custom fields in Phone Call record: Five9 Agent Name, Five9 Call Duration, Five9 After Call Work Time, Five9 Disposition, Five9 Queue/Skill, Five9 Transcript (for AI transcript), Five9 Summary (for AI summary). Provide screenshot documentation of all fields. Customer reviews for conflicts with existing customizations | Required | Not Started
REQ-071 | NetSuite Integration | Feature | Phone Call Activity Logging | Every inbound and outbound call automatically creates Phone Call activity record in NetSuite. Call records created in real-time as call connects to agent. Records include: Title/Subject (auto-generated), Phone number (ANI), Date/Time, Assigned To (agent), Status (Completed after call ends), Related Customer/Contact (linked if phone matched) | Required | Not Started
REQ-072 | NetSuite Integration | Feature | Custom Five9 Fields Population | Automatically populate custom fields: Agent Name (full name), Call Duration (total talk time in min/sec), After Call Work Time (wrap-up/disposition time), Disposition (disposition code selected), Queue/Skill (Finance, CS Place Order, CS Questions), Campaign (phone number/line customer called) | Required | Not Started
REQ-073 | NetSuite Integration | Feature | Phone Call Record Linking | If phone number matches Customer record: Phone Call linked to Customer ¦ If phone matches Contact record: Phone Call linked to Contact ¦ If agent manually selects different record during call: Phone Call linked to agent-selected record ¦ Link visible in 'Related Records' section under 'Five9 Tasks' subtab | Required | Not Started
REQ-074 | NetSuite Integration | Feature | ANI Lookup and Screen Pop - Single Match | When inbound call arrives: Five9 adapter performs real-time lookup in NetSuite. Searches Customer records AND Contact records for phone number match. If exactly ONE match found (one Customer OR one Contact): NetSuite automatically opens matched record in browser tab. Agent immediately sees customer/contact details, no manual search required | Required | Not Started
REQ-075 | NetSuite Integration | Feature | ANI Lookup and Screen Pop - Multiple Matches | If phone number matches multiple Customer records, multiple Contact records, or combination: NetSuite does NOT automatically open any record. Five9 adapter displays list of matching records as clickable hyperlinks with customer/contact names. Agent clicks appropriate record from list. Selected record opens in NetSuite browser tab | Required | Not Started
REQ-076 | NetSuite Integration | Feature | ANI Lookup and Screen Pop - No Match | If phone number not found in NetSuite: No screen pop occurs. Agent manually searches for customer by name, email, or other identifier. Agent creates new Customer/Contact record if first-time caller | Required | Not Started
REQ-077 | NetSuite Integration | Feature | ANI Lookup and Screen Pop - Mixed Match | If phone number matches one Customer record AND one Contact record: Treated as multiple matches. Adapter displays both options as clickable hyperlinks. Agent selects appropriate record based on context. Selected record opens in NetSuite | Required | Not Started
REQ-078 | NetSuite Integration | Feature | Click-to-Dial Functionality | All phone number fields in NetSuite Customer and Contact records become clickable. Clicking phone number initiates outbound call through Five9. Agent must be logged into Five9 agent desktop. Call placed through agent's configured phone (soft phone or physical phone). Outbound call automatically logged as Phone Call activity in NetSuite and linked to Customer/Contact from which click originated | Required | Not Started
REQ-079 | NetSuite Integration | Feature | Multi-Number Click-to-Dial Handling | If Customer/Contact has multiple phone numbers (office, mobile, home): Each number becomes individually clickable. Phone Call record notes which specific number was dialed | Required | Not Started
REQ-080 | NetSuite Integration | Interface | Five9 Adapter Browser Extension | Browser extension installed in Google Chrome or Microsoft Edge. Appears as sidebar panel on left side of NetSuite interface. Always visible when NetSuite is open (can be collapsed if needed) | Required | Not Started
REQ-081 | NetSuite Integration | Interface | Adapter Display During Call | Display: Agent status (Ready, Not Ready, etc.), Active call information (caller number, wait time, queue), Call controls (hold, transfer, conference, hang up), Disposition drop-down menu, Wrap-up/After Call Work timer, Customer/Contact matching information (if multiple matches found) | Required | Not Started
REQ-082 | NetSuite Integration | Interface | Adapter Display Between Calls | Display: Agent status controls, Call history (recent calls handled), Statistics (calls handled today, average handle time, etc.), Quick access to change status or request supervisor assistance | Required | Not Started
REQ-083 | NetSuite Integration | Interface | Multiple Match Hyperlinks Display | When phone number matches multiple NetSuite records: Adapter displays list of all matches as hyperlinked customer/contact names. Agent clicks appropriate name. NetSuite opens selected record in browser tab. Subsequent call log links to selected record | Required | Not Started
REQ-084 | NetSuite Integration | Feature | AI-Generated Transcript and Summary | Five9 records all calls and generates AI-powered transcript (verbatim text of conversation) and summary (AI-generated highlights and key points). Data written to custom fields (Five9 Transcript Field, Five9 Summary Field) in Phone Call activity record in NetSuite. Fields appear in Phone Call record detail view (may be large text/memo fields) | Optional | Not Started
REQ-085 | NetSuite Integration | Feature | Transcript/Summary Timing and Availability | Transcript and summary generated AFTER call ends and agent completes disposition. Processing time: Typically 30 seconds to 5 minutes. Data appears in NetSuite Phone Call record automatically. Agent may need to refresh NetSuite record to see newly populated data. No manual action required by agent - fully automatic | Optional | Not Started
REQ-086 | NetSuite Integration | Technical | OAuth2 Authentication Challenge - Decision Required | CRITICAL: NetSuite mandated migration to OAuth2. OAuth2 access tokens expire after 30 days. Five9 cannot maintain persistent machine-to-machine OAuth2 connection. Without active connection, transcript/summary will NOT write to NetSuite. Customer must choose solution approach during technical meeting with Angie (NetSuite admin), Dan, Nicole, Michelle, Gabriel, Sal | Required | Not Started
REQ-087 | NetSuite Integration | Technical | OAuth2 Solution Option 1 - Manual Token Refresh | Standard approach: Customer NetSuite admin (Angie) creates OAuth2 integration in NetSuite → Generates client ID/secret → Provides to Five9 → Every 30 days: Admin obtains grant code from Five9-provided URL → Enters grant code in Five9 Admin → Five9 exchanges for new access token. Requires: Admin with OAuth2 permissions, Calendar reminder for 30-day refresh, Five9-provided documentation. Transcript/summary feature dependent on this | Optional | Not Started
REQ-088 | NetSuite Integration | Technical | OAuth2 Solution Option 2 - Third-Party Middleware | Alternative: Deploy integration platform (e.g., Boomi, MuleSoft) → Platform maintains OAuth2 connection with NetSuite → Handles automatic token refresh → Five9 sends transcript/summary to platform via API → Platform writes to NetSuite. Requires: Integration platform license, Customer develops/configures integration flow, IT team maintains platform. Additional cost and complexity but eliminates manual 30-day refresh | Optional | Not Started
REQ-089 | NetSuite Integration | Access | NetSuite User Access Requirements | All agents using Five9/NetSuite integration must have: NetSuite user licenses, Appropriate NetSuite role permissions (view/edit Customer, Contact, Phone Call records), Five9 agent licenses, Browser extension installation permissions (Chrome/Edge). Customer responsible for provisioning user access. Five9 provides user count and permission requirements checklist | Required | Not Started
REQ-090 | Recording Prompts | Content | Holiday Messages | Option 1 - Universal holiday greeting (single message for all holidays): 'Our offices are closed today in observance of a company holiday. Please leave a message and we will return your call on our next business day.' OR Option 2 - Holiday-specific greetings (unique message per holiday): New Year's Day message, MLK Day message, Good Friday message, Memorial Day message, [Additional holidays per customer list]. Customer to specify preferred approach | Required | Not Started
REQ-091 | Recording Prompts | Content | Finance Greeting | Plays immediately when call enters Finance queue. Example: 'Thank you for calling the Finance department at [Company]. Your call is important to us. Please remain on the line and the next available representative will assist you.' Customer provides final script | Required | Not Started
REQ-092 | Recording Prompts | Content | Customer Service Greeting/Menu | Plays at IVR menu presentation. Example: 'Thank you for calling [Company] Customer Service. For Finance and billing questions, press 1. To place an order, press 2. For order status or other questions, press 3.' Customer provides final script | Required | Not Started
REQ-093 | Recording Prompts | Content | Finance After-Hours Message | Line-specific message. Example: 'Thank you for calling the Finance department at [Company]. Our offices are currently closed. Our business hours are Monday through Friday, 8:00 AM to 5:00 PM Eastern Time. Please leave a message and we will return your call on our next business day.' Customer provides final script | Required | Not Started
REQ-094 | Recording Prompts | Content | Customer Service After-Hours Message | Line-specific message. Example: 'Thank you for calling [Company] Customer Service. Our offices are currently closed. Our business hours are Monday through Friday, 8:00 AM to 7:00 PM Eastern Time. Please leave a message and we will return your call on our next business day. You may also place orders on our website at [URL].' Customer provides final script | Required | Not Started
REQ-095 | Recording Prompts | Content | Hold Announcements | First hold announcement (18 sec): 'All of our representatives are currently assisting other customers. Your call will be answered in the order it was received. Please remain on the line.' ¦ High call volume announcement: 'We are experiencing higher than usual call volume. Your call is important to us. Press 1 at any time to leave a voicemail message and we will return your call as soon as possible.' ¦ Optional estimated wait time announcement (if wait time engine enabled) | Required | Not Started
REQ-096 | Recording Prompts | Content | Temporary Closure Messages | Company meeting template: 'Thank you for calling [Company]. We are currently closed for a company meeting from 11:30 AM to 12:00 PM Eastern Time. Please leave a message and we will return your call after our meeting.' ¦ Generic template: 'Thank you for calling [Company]. We are temporarily closed. We will reopen at approximately [TIME]. Please leave a message or try your call again later.' Customer provides specific wording | Required | Not Started
REQ-097 | Recording Prompts | Content | Emergency Broadcast Messages | Customer will provide specific wording based on emergency type (weather, outage, etc.). Example: 'Thank you for calling [Company]. We are currently experiencing severe weather conditions in our area. You may experience delays in service. For immediate assistance, please visit our website at [URL] or email us at [address]. Please remain on the line to speak with an agent.' | Required | Not Started
REQ-098 | Recording Prompts | Content | Error Handling Messages | Invalid menu selection: 'I'm sorry, that is not a valid selection. Please try again.' ¦ Menu timeout: 'I'm sorry, I didn't receive your selection. Please listen carefully to the following options.' | Required | Not Started
REQ-099 | Recording Prompts | Technical | Audio Format Requirements | File Format: WAV (Waveform Audio File) ¦ Codec: G.711 μ-law (CCITT μ-law/PCMU) ¦ Bit Rate: 8-bit ¦ Sample Rate: 8000 Hz (8 kHz) ¦ Channels: Mono (single channel). Conversion process: Record in any format → Upload to G711.org converter (free) → Select 'Convert to WAV, mono, CCITT μ-law' → Download converted file → Submit to Five9 | Required | Not Started
REQ-100 | Recording Prompts | Quality | Recording Quality Standards | Clear, professional voice talent (male or female per customer preference). No background noise or echo. Consistent volume level across all prompts. Natural pacing (not too fast or slow). Professional tone appropriate for business context | Required | Not Started
REQ-101 | Recording Prompts | Implementation | Phase 1 - Testing with Text-to-Speech | Method: Five9 text-to-speech for all prompts during UAT. Sal creates text-to-speech versions based on customer-provided scripts. Text easily modified during testing without re-recording. Quality sufficient for functional testing but NOT professional enough for production. Customer requirement: Provide prompt scripts in Excel spreadsheet format | Required | Not Started
REQ-102 | Recording Prompts | Implementation | Phase 2 - Professional Recordings for Production | Method: Professional recordings in G.711 format. All professional recordings must be provided BEFORE go-live. Text-to-speech is temporary solution for testing only. Exception: Emergency broadcast messages may use text-to-speech in production for flexibility (customer decision) | Required | Not Started
REQ-103 | Recording Prompts | Deliverable | Customer Prompt Scripts Spreadsheet | Responsible: Michelle Corbett. Deliverable: Excel spreadsheet with columns: Prompt Name (e.g., 'Finance Greeting', 'Holiday Message'), Prompt Text/Script (exact wording to be recorded), Usage Context (where/when prompt plays in call flow), Special Instructions (emphasis, pacing, tone guidance). Required before IVR build begins | Required | Not Started
REQ-104 | Phone Numbers | Provisioning | Additional Phone Number Request | Current state: ONE test phone number provisioned (insufficient for testing two distinct lines). Requirement: Two (2) additional phone numbers for testing and production. Assignment: One number for Finance line, One number for Customer Service line. Type: Toll-free numbers preferred (800/888/877/866/855/844/833 prefix); geographic local numbers acceptable if toll-free unavailable | Required | Not Started
REQ-105 | Phone Numbers | Provisioning | Phone Number Provisioning Process | Gabriel notified Account Executive (Angelina Sena). Angelina sends email to Dan Callari with: Number request form/procurement process, Pricing information (if applicable), Estimated delivery timeline, Customer decision points (vanity number options). Numbers required before IVR testing phase. Customer must respond promptly to avoid delays | Required | Not Started
REQ-106 | Phone Numbers | Configuration | Number Mapping to Lines | Once provisioned: Number 1 assigned to Finance campaign/line (routes to Finance call flow, DID/DNIS used in reporting) ¦ Number 2 assigned to Customer Service campaign/line (routes to CS call flow, DID/DNIS used in reporting) | Required | Not Started
REQ-107 | Phone Numbers | Testing | Phone Number Testing Requirements | Both numbers fully testable during UAT. Test scenarios: Call each number during business hours, Call each number after hours, Test IVR menu options (CS number), Test voicemail functionality on both numbers, Test NetSuite screen pop with calls to each number | Required | Not Started
REQ-108 | Phone Numbers | Future | Legacy Number Migration (Future Phase) | Customer has multiple legacy 800 numbers routing to old ICE system. Future requirement (post-implementation): All existing customer-facing phone numbers ported/routed to Five9. Legacy numbers route to Customer Service line (catch-all). Number porting is separate project phase - NOT in initial implementation scope. Customer to provide complete list of legacy numbers. Separate timeline and testing required | Optional | Not Started
REQ-109 | Training | Agent Training | Five9 Agent Desktop Training | Training on: Logging in/out, Understanding agent states (Ready, Not Ready, ACW), Answering inbound calls, Placing calls on hold, Transferring calls (warm/cold transfer), Conferencing calls, Dispositioning calls, Accessing voicemail queue ('Ready - All' status), Playing and processing voicemail messages, Making outbound calls (manual dial and click-to-dial from NetSuite) | Required | Not Started
REQ-110 | Training | Agent Training | NetSuite Integration Training | Training on: Understanding screen pop behavior (single match vs multiple matches), Selecting correct customer/contact from multiple match list, Using click-to-dial functionality from NetSuite records, Viewing logged call activity in NetSuite, Understanding custom Five9 fields in Phone Call records, Accessing transcript and summary data (if feature implemented) | Required | Not Started
REQ-111 | Training | Agent Training | Call Handling Procedures Training | Training on: Appropriate greetings based on queue/line (Finance vs CS Place Order vs CS Questions), Handling transferred calls (from CS IVR to Finance), Procedures for complex calls requiring transfer, Voicemail callback procedures and prioritization, Escalation procedures for issues beyond agent authority | Required | Not Started
REQ-112 | Training | Supervisor Training | Supervisor Functionality Training | Training on: Monitoring agent performance (dashboards and reports), Real-time queue monitoring, Assisting agents remotely (barge, whisper, coach functions), Running standard reports, Understanding key metrics and KPIs | Required | Not Started
REQ-113 | Training | Administrator Training | Administrator System Management Training | Training on: Updating IVR prompts (text-to-speech editing), Activating/deactivating emergency broadcasts, Creating/modifying temporary closure schedules, Managing holiday schedules, Uploading new recording prompts, Creating new agent users, Assigning agents to queues/skills, Creating/modifying disposition codes, Basic troubleshooting, NetSuite OAuth2 token refresh process (if using manual refresh option) | Required | Not Started
REQ-114 | Training | Delivery | Training Session Logistics | Format: Live virtual training sessions via Zoom/WebEx with screen sharing and hands-on practice in sandbox environment. Recorded sessions for future reference and new hire training. Participants: All agents (Finance and CS teams), All supervisors/managers, Designated administrators (Michelle, Nicole, others). Timing: Training scheduled after UAT completion, 1-2 weeks before go-live for practice time | Required | Not Started
REQ-115 | Documentation | Deliverables | End-User Documentation | Provide: Agent quick reference guide, Supervisor guide, Administrator guide, Call flow diagrams finalized, Escalation procedures documented, OAuth2 refresh procedures documented (if applicable) | Required | Not Started
REQ-116 | Testing | UAT Scenarios | Finance Line During Business Hours Test | Call Finance number during business hours (8 AM - 5 PM Mon-Fri) → Verify Finance greeting plays → Verify call routes to Finance queue → Verify agent desktop shows 'Finance' indicator → Verify NetSuite screen pop (if phone in system) → Verify call logs in NetSuite as Phone Call activity → Agent dispositions call → Verify disposition appears in NetSuite Phone Call record | Required | Not Started
REQ-117 | Testing | UAT Scenarios | Finance Line After Hours Test | Call Finance number outside business hours → Verify after-hours message plays → Verify call routes to Finance voicemail → Leave test voicemail → Agent accesses voicemail via 'Ready - All' status → Verify voicemail plays correctly → Agent dispositions voicemail → Verify voicemail interaction logs in NetSuite | Required | Not Started
REQ-118 | Testing | UAT Scenarios | Finance Line Holiday Test | Configure test holiday → Call Finance number on test holiday → Verify holiday message plays → Verify call routes to Finance voicemail → Validate voicemail processing same as after-hours test | Required | Not Started
REQ-119 | Testing | UAT Scenarios | Finance Line Temporary Closure Test | Configure temporary closure schedule → Call Finance number during closure window → Verify temporary closure message plays → Verify call routes to voicemail → Deactivate temporary closure → Call again → Verify normal routing resumes | Required | Not Started
REQ-120 | Testing | UAT Scenarios | Customer Service Line Press 1 Test | Call CS number during business hours → Verify CS greeting/menu plays → Press 1 for Finance → Verify call transfers to Finance queue → Verify agent desktop shows 'Finance' → Complete call and verify logging | Required | Not Started
REQ-121 | Testing | UAT Scenarios | Customer Service Line Press 2 Test | Call CS number during business hours → Press 2 for Place Order → Verify call routes to CS Place Order queue → Verify agent desktop shows 'CS Place Order' → Verify only agents assigned to Place Order queue receive call → Complete call and verify logging | Required | Not Started
REQ-122 | Testing | UAT Scenarios | Customer Service Line Press 3 Test | Call CS number during business hours → Press 3 for Questions → Verify call routes to CS Questions queue → Verify agent desktop shows 'CS Questions' → Verify only agents assigned to Questions queue receive call → Complete call and verify logging | Required | Not Started
REQ-123 | Testing | UAT Scenarios | IVR Menu Error Handling Test | Call CS number → Press invalid digit (e.g., 4) → Verify error message plays → Press invalid digit again → Verify error message plays again → Press invalid digit third time → Verify call routes to default queue (CS Questions) → Complete call and verify logging | Required | Not Started
REQ-124 | Testing | UAT Scenarios | Hold Experience with Voicemail Option Test | Call Finance or CS during high-volume simulation (all agents busy) → Verify hold music plays for 18 seconds → Verify first announcement plays → Verify hold music plays for 30 seconds → Verify voicemail option announcement plays → Press 1 for voicemail → Verify immediate route to voicemail → Leave message and verify processing | Required | Not Started
REQ-125 | Testing | UAT Scenarios | Emergency Broadcast Activation Test | Admin calls internal broadcast control number → Activate emergency broadcast with test message → Call Finance number → Verify emergency message plays before normal greeting → Verify call continues through normal flow after broadcast → Call CS number → Verify same behavior → Deactivate emergency broadcast → Call both numbers again → Verify emergency message no longer plays | Required | Not Started
REQ-126 | Testing | UAT Scenarios | NetSuite Click-to-Dial Test | Agent logged into Five9 and NetSuite → Navigate to Customer record in NetSuite → Click phone number field → Verify Five9 initiates outbound call → Complete call → Verify call logs as Phone Call activity → Verify Phone Call record links to Customer | Required | Not Started
REQ-127 | Testing | UAT Scenarios | NetSuite Multiple Match Test | Create two test Customer records with identical phone number → Have test caller call that phone number → Verify NO automatic screen pop → Verify Five9 adapter shows hyperlinks for both matching customers → Agent clicks one hyperlink → Verify correct Customer record opens → Verify call logs and links to agent-selected Customer | Required | Not Started
REQ-128 | Testing | Go-Live Readiness | System Configuration Checklist | All IVR call flows configured and tested ✓ All queues configured with correct agents assigned ✓ All holiday schedules configured ✓ All professional recordings uploaded and tested ✓ NetSuite integration fully functional ✓ OAuth2 connection established (if using transcript/summary) ✓ All phone numbers provisioned and tested ✓ Emergency broadcast feature tested and documented | Required | Not Started
REQ-129 | Testing | Go-Live Readiness | Training Completion Checklist | All agents trained and comfortable with Five9 desktop ✓ All agents trained on NetSuite integration ✓ Supervisors trained on monitoring and reporting ✓ Administrators trained on system management | Required | Not Started
REQ-130 | Testing | Go-Live Readiness | Customer Sign-Off Requirements | Customer formally approves UAT test results ✓ Customer confirms all requirements met ✓ Customer agrees to go-live date ✓ Customer signs business requirements document | Required | Not Started
REQ-131 | Support | Hypercare | Hypercare Period Support | Duration: First 2 weeks after go-live. Support provided: Five9 implementation team on standby for immediate issue resolution, Daily check-in calls with customer for first 3-5 days, Rapid response to configuration adjustment requests, Real-time monitoring of call flows and queue performance | Required | Not Started
REQ-132 | Support | Optimization | Week 1-2 Performance Review | Analyze: Call volume patterns by line and queue, Agent handle times and after-call work times, Hold time averages and abandon rates, Voicemail volume and return rates, Any unexpected call flow issues | Required | Not Started
REQ-133 | Support | Optimization | Post-Launch Optimization Opportunities | Potential adjustments: Hold music/announcement intervals if needed, Queue timeout thresholds fine-tuning, Agent assignments to queues based on actual volume, IVR menu prompts if customer confusion detected, Temporary closure schedules based on actual usage | Required | Not Started
REQ-134 | Support | Ongoing | Ongoing Support Model Definition | Support channels: Five9 Technical Support (system issues, bugs, technical problems), Account Executive Angelina Sena (licensing, billing, account questions), Five9 Knowledge Base and Documentation (self-service). Customer responsibilities: Routine IVR prompt updates, Holiday schedule maintenance, Temporary closure management, Agent user management, OAuth2 token refresh (if manual refresh option). Five9 responsibilities: Platform uptime/performance, Bug fixes and patches, Feature enhancements/upgrades, Tier 2/3 technical support escalation | Required | Not Started